Hiawassee Downtown Development Authority

FUN-Draiser Committee Meeting Agenda

Date: 		Monday, March 9, 2026

Time:		9:00 AM

Location:	50 River Street, Upstairs Training Room

- Call to order – 9:04 AM

- Adopt agenda as set or amended – Nancy, Bradley, Approved

- FUN-Draiser Planning:

Day before: July 17 plan for a morning setup starting at 10 or 11AM

Event: July 18 plan on 2PM setup, and staying until 10PM

  - Food – VIP, Band, Food Trucks

    - The Ark – confirmed they want to do it

    - Taco truck from Blue Ridge – Bradley to send name

    - Coffee truck? – Serenity

    - VIP – Mama’s Concierge

    - Band – The Ark for meals, a volunteer will stock green room

    - Nancy can go to Sams for any bulk items

  - Silent Auction – Donations, Ticket Giveaways

    - Email a list of the silent auction donors and what they gave in 2025

    - Go out to businesses in pairs to solicit donations.

    - Add to the list:

      - John C Campbell Folk School and/or Olive’s Porch

      - True Colors Pottery

    - Deadline to tell businesses – June; Final final deadline – June 30

  - Wine Pull – Donations, Ticket Giveaways

    - Email out a list of the wine donors from last year and what they gave in 2025

    - Allow places to promote themselves on the bottles if they want to

    - Minimum bottle value $20; cork price at event is $15

    - Make an updated wine pull info flyer

  - Marketing – Direct Mail Postcard, Flyers, Ticket Giveaways, Digital Ads, AirBnBs, Hotels

    - Jinelle and Lily will do the direct mail postcard

    - Make a flyer for the ticket giveaways

    - Facebook page banner

    - AirBnBs – target property management companies that have multiple properties

    - Ask Rick Andrews if he’d advertise it

    - Get flyers to the Lake Chatuge Chamber – Shawn

  - 50/50 Raffle – License

    - Nancy can apply for this – Lily send tax ID

  - Swag Bags

    - Order items closer to the date – sold ~180 last year

    - We’ll have a volunteer night

  - Volunteers

    - Ask the City clerks if they’ll volunteer

    - Be thinking about

- Miscellaneous Items

  - Sponsors

    - BRMEMC sponsored at the $1,000 level

  - Press

    - Put out a press release about the PBC’s work so far, and promoting the concert

  - Cash/checkout table

    - Have DDA or City staff at this table

    - Look at getting a Square POS so it can do offline payments

  - Regular meeting time

    - Change regular meeting back to March 17, 2026 at 8:30 AM.

- Adjourn 9:55 AM